## ZXQ
类别 | 子类 | 节点数量 | 监控项个数 | 服务器端配置模板中每个配置项相关的工作量 | 第一个节点每个配置项的脚本工作量（人天） | 从第二个节点起每个配置项相关工作量（人天） | 子类工作量估计 | 实际参考 | 监控项 | 状态查询接口 | 状态查询接口示例 | 状态查询脚本 | 状态查询脚本示例 | 备注
数据库 | MySQL | 1 | 14 | 0.05 | 0.05 | 0.05 | 1.4 | 0.5 | MySQL begin operations per second
MySQL bytes received per second
MySQL bytes sent per second
MySQL commit operations per second
MySQL delete operations per second
MySQL insert operations per second
MySQL queries per second
MySQL rollback operations per second
MySQL select operations per second
MySQL slow queries
MySQL status
MySQL update operations per second
MySQL uptime
MySQL version
realtime calc RESTAPI
| MongoDB | 1 | 12 | 0.05 | 0.05 | 0.05 | 1.2 | 0.5 | connections_available
connections_current
database_info
db_collections
db_dataSize
db_fileSize
db_indexes
db_info
db_objects
db_storageSize
mem_bits
mem_resident
| Redis | 1 | 12 | 0.05 | 0.05 | 0.05 | 1.2 | 1 | Blocked_clients | lack of auth
Connected_clients
Connected_slaves
Connections_rate
Evicted_keys
Expired_keys
Port_status
Request_rate
Role
Uptime_in_seconds
Used_memory
Used_memory_rss
负载均衡 | LVS | 1 | [5 empty] | 1 | keepalived_status
lvs_stats_Conn
lvs_stats_InBytes
lvs_stats_InPkts
lvs_stats_OutBytes
lvs_stats_OutPkts
| HAProxy | 1 | 9 | 0.05 | 0.05 | 0.05 | 0.9 | 0.5 | current connections
HAProxy Version
Node Name
number of process
pipes free
pipes used
Running queue
task number
Uptime of HAProxy
| Tengine | 1 | 7 | 0.05 | 0.05 | 0.05 | 0.7 | 0.5 | accept
conn_active
conn_reading
conn_waiting
conn_writing
handled
request
存储 | Fastdfs | 1 | 5 | 0.05 | 0.05 | 0.05 | 0.5 | 1 | fdfs_status |  |  |  |  | OSS | 每个点都要配置自身IP, 2 tracker, 4 storage
fdfs_storage_free
fdfs_storage_total
fdfs_total_file_open_count
fdfs_total_upload_bytes
网络 | 公网 | [12 empty] | 因为服务器都是租的，由租赁方提供基础的CPU, 硬盘，内存及网络的监控
内网
专线
代理服务器
容灾中心备份 | 数据库 | [5 empty] | 1.9 |  | 备份情况（参考数据库部分及具体部署）
| 存储 | [5 empty] | 0.25 |  | 备份情况（参考存储部分及具体部署）
| Zookeeper | 1 | 16 | 0.15 | 0.15 | 0.05 | 4.8 | 4 | zk_version
zk_avg_latency
zk_max_latency
zk_min_latency
zk_packets_received
zk_packets_sent
zk_num_alive_connections
zk_outstanding_requests
zk_server_state
zk_znode_count
zk_watch_count
zk_ephemerals_count
zk_approximate_data_size
zk_open_file_descriptor_count
zk_max_file_descriptor_count
zk_running_ok
[8 empty] | 4 | Dubbo | running_status, stat | Yang, Jian, dubbo portal, restAPI |  | Screen link Dubbo portal URL, aliyun
[8 empty] | 4 | TBSchedule | Using its log system | Yin, Chun-lin: req spec, restAPI |  | Screen link URL
| RabbitMQ | 1 | 4 | 0.05 | 0.1 | 0.05 | 0.6 | 0.5 | rabbit_conn_proc
rabbit_node_stats
rabbit_queue_proc
rabbit_total_memory
| ESB | 1 | 4 | 0.5 | 0.5 | 0.05 | 4 | 6 | 假设4个监控项
假设4个监控项
假设4个监控项
假设4个监控项
| LogStash | 1 | 4 | 0.5 | 0.5 | 0.05 | 4 | 2 | LS_status
LS_node_status
| ES | 1 | 5 | 0.5 | 0.5 | 0.05 | 5 | 2 | ES_connections
ES_status
ES_insert
ES_query
ES_mem
| Kibana | 1 | 4 | 0.5 | 0.5 | 0.05 | 4 | 2 | 假设4个监控项
假设4个监控项
假设4个监控项
假设4个监控项
| Tomcat | [6 empty] | 3 | ji,zhe; FeiHu
短信 | 短信 | 1 | 4 | 0.5 | 0.5 | 0.05 | 4 | 2 | 平台运行状态（服务器提供） | 假设提供URL
[9 empty] | 容量 | 假设提供URL,自己配置python脚本读取本月配额及已发送条数
[9 empty] | 发送情况 | 假设提供URL
[9 empty] | 日志查询？ | 假设提供URL
外呼 | 外呼 | 1 | 4 | 0.5 | 0.5 | 0.05 | 4 | 2 | 平台运行状态（服务器提供） | 假设提供URL
[9 empty] | 容量 | 假设提供URL
[9 empty] | 状态？（呼叫情况） | 假设提供URL
[9 empty] | 日志查询？ | 假设提供URL
其他工作量评估参数 | 工作量 | 个数 | 小计
集成测试与单元开发所花时间的比率 | 0.05 | 1 | 1
容灾中心服务器数量与生产中心的比率 | 0.5
定制通知手段 | 1.5 | 1 | 1.5
定制通知动作 | 0.05 | 105 | 5.25
拓扑定制所花时间 | 1.5 | 1 | 1.5
面板定制 | 1 | 3 | 3
报表定制 | 0.4 | 16 | 6.4
服务器安装及部署 | 1 | 3 | 3
总工作量预估 | 61.0225 |  |  | 56
与应用集群owner的沟通,可能有些需求现在没想到
Ji,Zhe
Linux，杜明海
系统，网络，中间件，应用
desc, threshould

## TBD
Auth
Logon Status
Vehicle activity
Key mgmt